## Combined
Reference | Infrastructure Type | Scheme | Prioritisation | Cost | Confirmed Funding | Delivery Body | Delivery Phasing | District Area | Source
Transport
T1 | Highways | Various minor works to the A34, including lay-by improvements, increased signage, improvements to the cycle track along the Western bypass and various other safety improvements | Important | Dependent on scope and scale |  | Highways England | 2021-2026 | Central and West Oxford | Stakeholder engagement with Highways England
T2 | Highways | Zero Emission Zone (Phase I) Pilot Implemented | Essential | 300000 | 300000 | Oxford City and Oxfordshire County Councils | 2021-2026 | City-Wide | OxIS (2017)/ OTS
T3 | Highways | Zero Emission Zone (Phase II) | Critial | 1000000 |  | Oxford City and Oxfordshire County Councils | 2021-2026 | City-Wide | OxIS (2017) OxIS (2022)
T4 | Highways | Traffic Filters and Supporting Measures for Core Scheme. Outline Business Case is being funded by the Growth Deal. | Critical | £3000000 | Some scheme costs secured against future income. £500,000 shortfall. | Oxfordshire County Council | 2021-2026 | City-Wide | OTS and Stakeholder engagement with Oxfordshire County Council
T5 | Rail | Oxford Rail Corridor Phase 2, including additional platform at Oxford Railway Station, secondary station entrance, replacement of Botley Road Bridge, closure of Yarnton Lane and Sandy Lane level crossings, new high-speed track crossovers at Oxford North Junction, and upgrade of multi-modal interchange (e.g. bus provision and cycle parking) | Essential | £69,000,000 (Network Rail) | Funded in full (DfT) | Network Rail | 2021-2026 | Central and West Oxford | Oxfordshire Rail Corridor Study
T6 | Rail | Cowley Branch Line passenger reopening to include two new passenger statons. Improvements to mainline track capacity south of Oxford Station and likely additional track around Hinksey. Network Rail undertaking GRIP Study to determine costs. The Growth Deal will contribute towards complementary development work, and there is £50,000 committed funding from CIL for feasibility studies. | Essential | TBC | £50,000 CIL funding | Network Rail | 2026-2031 | Cowley Littlemore | Oxfordshire Rail Corridor Study
T7 | Rail | Potential for new railway station at Begbroke, to connect with the Science Park, and perhaps North Cotswold Line | Important | Dependent on scope and scale |  | Network Rail | 2026-2036 | Cherwell District | Oxfordshire Rail Corridor Study
T8 | Bus | Orbital bus route between Cowley and Hinksey connecting the city centre, Science Vale and Didcot. Delivered as part of wider package to deliver bus priority in the Eastern Bypass (£158m) | Essential | Dependent on scope and scale |  | Oxfordshire County Council | 2022-2031 | Central and West Oxford, South Oxford | Stakeholder engagement with Oxfordshire County Council
T9 | Highways | Workplace Parking Levy (WPL) to encourage sustainable transport use . Outline Business Case is being funded by the Growth Deal. | Critical | 600000 | Borrowing against future income from scheme | Oxfordshire County Council | 2021-2026 | City-Wide | OTS
T10 | Active Travel Bus | City Centre Corridor Improvements (West – Hythe Bridge St/ Oxpens Rd/ George St/ New Road), including active travel improvements, linked to LCWIP route CE2 proposal | Essential | tbc |  | Developers | 2022 - 2036 | Central and West Oxford | OxIS (2017) / LCWIP
T11 | Active Travel Bus | City Centre Corridor Improvements (North – St Giles/ Magdalen St/ Broad St, including active travel improvements linked to the LCWIP route CN1 proposals | Essential | tbc |  | Oxfordshire County Council/Developers | 2021-2026 | Central and West Oxford | OxIS (2017)/ OTS / LCWIP
T12 | Active Travel Bus | City Centre Corridor Improvements (South & East – High St/ St Aldates), including active travel improvements linked to LCWIP route CE1 | Essential | tbc |  | Oxfordshire County Council | 2021-2026 | Central and West Oxford | OxIS (2017)/ OTS / LCWIP
T13 | Active Travel Bus Highways | Banbury Road Corridor Improvements between Cutteslowe and St Giles, including active travel improvements linked to LCWIP route 4 proposal | Essential | 18000000 |  | Oxfordshire County Council | 2021-2026 | North Oxford | OxIS (2017) / LCWIP
T14 | Active Travel Bus Highways | Woodstock Road Corridor Improvements, including active travel improvements linked to LCWIP route 3 proposal. In receipt of Growth Deal forward funding. | Essential | £18000000 | 12500000 | Oxfordshire County Council | 2021-2026 | North Oxford | OxIS (2017) / LCWIP
T15 | Active Travel Bus Highways | Abingdon Road Corridor Improvements, from Folly Bridge to Kennington Roundabout | Essential | 17606000 |  | Oxfordshire County Council | 2021-2031 | South Oxford | OxIS (2017) / Oxford City Council identified scheme
T16 | Active Travel Bus Highways | Cowley Road/ Garsington Road/ Watlington Road Corridor Improvements, from Magdalen Road to Grenoble Road, including improvements to Cowley Interchange and active travel improvements linked with route 14 of the LCWIP | Essential | 31187000 |  | Oxfordshire County Council/Developers | 2021-2031 | South Oxford | OxIS (2017) / LCWIP
T17 | Active Travel Bus Highways | Iffley Road Corridor Improvements, from The Plain to Littlemore roundabout, including active travel improvements linked with LCWIP route 17. | Essential | 18048000 |  | Oxfordshire County Council | 2021-2031 | South Oxford | OxIS (2017) / LCWIP
T18 | Active Travel Bus Highways | B4495 Corridor Improvements (Hollow Way/ Between Towns Road/ Donnington Bridge). B4495 Access to Headington funded through the Growth deal. | Essential | 32046000 |  | Oxfordshire County Council | 2021-2031 | South Oxford | OxIS (2017)
T19 | Active Travel Bus Highways | London Road Corridor Improvements, between St Clements and Green Road roundabout | Essential | 17155900 |  | Oxfordshire County Council | 2021-2031 | East Oxford | OxIS (2017) / OTS / LCWIP
T20 | Bus | Park and Ride Service serving Eynsham Garden Village, linking to Oxford via a near continuous bus lane on the A40 | Important | £2.97m |  | Apportioned between developments | 2026-2036 | Central and West Oxford, North Oxford, West Oxfordshire District | Stakeholder engagement with Oxfordshire County Council
T21 | Bus | Extension of existing bus routes (funding for additional vehicles) into Bayswater Brook site in South Oxfordshire, linking to City Centre and Eastern Arc | Important | Dependent on scope and scale |  | Oxfordshire County Council | 2026-2036 | Central and West Oxford, East Oxford, South Oxfordshire District | Stakeholder engagement with Oxfordshire County Council
T22 | Bus | Extension of existing bus routes (funding for additional vehicles) into Northfield site in South Oxfordshire, linking to City Centre and Science Vale | Important | Dependent on scope and scale |  | Oxfordshire County Council | 2026-2036 | Central and West Oxford, South Oxford, South Oxfordshire District | Stakeholder engagement with Oxfordshire County Council
T23 | Active Travel Highways | Low traffic neighbourhoods. Oxfordshire County Council assumes that Assumption that 6 LTNs will be necessary by 2025/2026 and 2 additional LTNs will be necessary by 2030. | Essential | 8000000 | £50,000 committed through the Active Travel fund awarded by central Government, £200,000 committed through Tranche 2 | Oxfordshire County Council | 2021-2026 | City-Wide | LCWIP and Stakeholder engagement with Oxfordshire County Council
T24 | Highways | Controlled Parking Zones (city-wide) | Essential | £1,000,000 |  | Oxfordshire County Council | 2022 - 2026 | City-Wide | LCWIP and City/ County Capital Programmes
T25 | Bus Highways | Provision of additional coach parking within the city | Essential |  |  | City and County Councils | 2021-2031 | City-Wide | OxIS (2017)
T26 | Highways | Introduction of a scheme of pilot freight vehicle restrictions within the city centre | Essential | 50000 |  | Oxfordshire County Council | 2021-2026 | City-Wide | OxIS (2017)
T27 | Active Travel | District Centre Improvements (All Centres)/Mobility Hubs | Important |  |  | Oxfordshire County Council | 2021-2026 | City-Wide | Oxford Transport Strategy
T28 | Highways | Northern Gateway site-link road | Critical | Fully funded via LGF2 | Fully funded via LGF2 | “Oxford North” | 2021-2023 | North Oxford | OxIS (2017)
T29 | Highways | Horspath Road Junction Improvements | Essential |  |  | Oxfordshire County Council | 2016-2031 | South Oxford | OxIS (2017)
T30 | Bus | John Radcliffe Hospital on-site bus interchange & priority measures | Essential | 3000000 |  | Oxfordshire County Council | 2021-2026 | East Oxford | OxIS (2017)
T31 | Active Travel Bus | Churchill Hospital additional bus & cycle access | Essential | 2000000 |  | Oxfordshire County Council | 2021-2026 | East Oxford | OxIS (2017)
T32 | Active Travel | Cycle lane through the residential area parallel with Abingdon Road, linking with Osney Mead, linked to active travel improvements in route 20 of the LCWIP | Essential | 12035000 |  | Oxfordshire County Council | 2021-2026 | South Oxford / Central and West Oxford | Oxford City Council identified scheme / LCWIP
T33 | Highways | Redbridge park and Ride Electric Vehicle supercharging point | Important | Dependent on scope and scale |  | Oxfordshire County Council | 2021-2026 | South Oxford | Oxford City Council identified scheme
T34 | Active Travel | Active travel network improvements in Blackbird Leys, including linkages across the Cowley Branch Line | Important | Dependent on scope and scale |  | Oxfordshire County Council | 2021-2026 | South Oxford | Oxford City Council identified scheme
T35 | Active Travel | Improvements to cycling provision along Botley Road, including active travel improvements linked to route 25 of the LCWIP. Growth Deal funding contributions to support the feasibility works on widening the Botley Road Railway Bridge. | Essential | 19590000 | 9100000 | Oxfordshire County Council / Growth Deal | 2021-2026 | Central and West Oxford | Oxford City Council identified scheme / LCWIP
T44 | Active Travel | A40 cycle bridge schemes helping to link Bayswater and Barton Park developments to existing cycle network, as well as providing pedestrian access out for residents | Critical | Dependent on scope and scale |  | Landowners | 2021-31 | East Oxford, South Oxfordshire District | Oxford City Council identified scheme
T46 | Highways | Go Ultra Low Oxford Project - electric vehicle charging solutions for residents who do not have off-street parking | Important | Dependent on scope and scale |  | Oxford City Council / Oxfordshire County Council | 2021-2026 | City-Wide | Oxford City Council identified scheme
T47 | Active Travel | Improve pedestrian and cycle links to wider strategic routes into and out of the city from Summertown District centre, as identified in the Local Plan, including the delivery of cycle stands for public cycle parking within Diamond House and Ewert House. | Essential | Dependent on scope and scale |  | Delivered through development at Summertown District Centre | 2026-2036 | North Oxford | Policy AOC5: Summertown District Centre, Oxford Local Plan and Policy SP6: Diamond Place and Ewert House, Oxford Local Plan
T48 | Active Travel | Pedestrian and cycle access across the whole allocated site at Old Road Campus as identified within the Local Plan, at route 12 of the LCWIP. This scheme is being funded through the Growth Deal. | Critical | Dependent on scope and scale |  | Delivered through development at Old Road Campus | 2026-2036 | East Oxford | Policy SP21: Old Road Campus, Oxford Local Plan / LCWIP
T49 | Active Travel | Potential bridge over the River Thames to link to East Oxford via Jackdaw Lane, including widening and resurfacing of the cycle path and addition of solar lighting | Important | 5000000 |  | Oxfordshire County Council | 2026-2031 | South Oxford | LCWIP
T50 | Active Travel | A40 Pedestrian Crossing at Collinwood Road, currently at design feasibility stage | Essential | 750000 |  | Oxfordshire County Council | 2021-2026 | East Oxford | LCWIP
T51 | Bus | Extension of Thornhill Park and Ride by 465 spaces | Important | 2800000 |  | Oxfordshire County Council | 2021-2026 | East Oxford | Draft OxIS Stage 1 Technical Report for Consultation
T52 | Rail | Oxford Canal Rail Junction - provision of crossover between Up and Down Bletchley Lines, providing additional capacity and resilience | Important | Dependent on scope and scale |  | Network Rail | 2031-2036 | North Oxford | Draft OxIS Stage 1 Technical Report for Consultation
T53 | Active Travel | Improvements to North Oxford Cycle Route, to address pinchpoints and provide surfacing improvements. The majority of this route is along the highway network, but some sections are on third party land, including active travel improvements linking with LCWIP route 5 | Essential | 3000000 |  | Oxfordshire County Council | 2026-2031 | North Oxford | LCWIP
T54 | Active Travel | LCWIP Route 1: Canal Path, including the Canal Towpath Extension and Cycle bridge over the Canal linking Nelson Street to the Station. Funded by Growth Deal. | Essential | 2500000 | 2500000 | Oxfordshire County Council / Growth Deal | 2021-2026 | Central and West Oxford | LCWIP
T55 | Active Travel | LCWIP Route 2: Walton Street calming and filtering interventions, and Walton Street Shopping QPC | Essential | 1210000 |  | Oxfordshire County Council | 2021-2026 | Central and West Oxford | LCWIP
T56 | Active Travel | LCWIP Route 3: Wolvercote Roundabout Crossing | Essential | 1825000 |  | Oxfordshire County Council | 2021-2026 | North Oxford | LCWIP
T57 | Active Travel | LCWIP Route 6: Marston, including improvements to the lighting, and upgrades to the bridge, as well as the Marston QPC | Essential | 850000 |  | Oxfordshire County Council | 2021-2026 | East Oxford | LCWIP
T58 | Active Travel | LCWIP Route 7: Marston Road, including the crossing from Copse Lane to Marston Road | Essential | 200000 |  | Oxfordshire County Council | 2021-2026 | East Oxford | LCWIP
T59 | Active Travel | LCWIP Route 8: Northway & Barton, including the widening of the subway to Barton and a new path link | Important | 1000000 |  | Oxfordshire County Council | 2021-2026 | East Oxford | LCWIP
T60 | Active Travel | LCWIP Route 9: Headington Path, improvements to the street lighting and paths | Important | 600000 |  | Oxfordshire County Council | 2021-2026 | East Oxford | LCWIP
T61 | Active Travel | LCWIP Route 11: Quarry and Risinghurst Route Improvements | Essential | 200000 |  | Oxfordshire County Council | 2021-2026 | East Oxford | LCWIP
T62 | Active Travel | LCWIP Route 12: Old Road, including the extension of the A2H scheme at Old Road, and improvements to Wheatley - Oxford via Shotover, and Morrell Avenue / Warneford Lane (St Clements - Old Road), and the Old Road QPC | Essential | 7035000 |  | Oxfordshire County Council / Growth Deal | 2021-2026 | East Oxford / South Oxfordshire District | LCWIP
T63 | Active Travel | LCWIP Route 13: Barracks Lane and Horspath, including surface improvements, widening and removal of barriers at Barracks Lane, a cycle link at Pony Road, and average speed cameras, as well as the Horspath QPC | Essential | 3085000 |  | Oxfordshire County Council | 2021-2026 | City-Wide | LCWIP
T64 | Active Travel | LCWIP Route 15: Blackbird Leys, including a link road from Maidstone Road - Barns Road, and various improvements to Barns Road, as well as BBL shopping Street redesign, and the Barns Road QPC | Essential | 9389000 |  | Oxfordshire County Council | 2021-2026 | South Oxford | LCWIP
T65 | Active Travel | LCWIP Route 16: Littlemore, including route improvements and a protected crossing of Church Cowley Road, and the Iffley Road QPC | Essential | 1525000 |  | Oxfordshire County Council | 2021-2026 | South Oxford | LCWIP
T66 | Active Travel | LCWIP Route 18: Rose Hill, including route improvements and improvements to Cottesmore Bridge - Ringroad | Essential | 2200000 |  | Oxfordshire County Council | 2021-2026 | South Oxford | LCWIP
T67 | Active Travel | LCWIP Route 21: South Oxford Path, including surfacing improvements to the South Oxford Cycle Route, replacement of the Pipe bridge and new cycle track by slip road, as well as pedestrian improvements to Bartholomew Road, and the Upper Road Kennington Access QPC | Essential | 6800000 |  | Oxfordshire County Council | 2021-2026 | South Oxford | LCWIP
T68 | Active Travel | LCWIP Route 22: South Hinksey Path. Full detail subject to final build-out of Oxford Flood Alleviation Scheme. | Important | Subject to scope and scale |  | Oxfordshire County Council | 2026-2031 | South Oxford | LCWIP
T69 | Active Travel | Improvement of footpath from River Thames through Bulstake, linked to Ferry Hinksey Road and Botley Road, linked with Route 23 of the LCWIP. | Essential | 460000 | 330000 | Oxfordshire County Council / Growth Deal | 2021-2026 | Central and West Oxford | LCWIP / Oxford City Council identified scheme
T70 | Active Travel | LCWIP Route 24: West Oxford Path, including surfacing and widening improvements at Oatlands Park | Essential | 120000 |  | Oxfordshire County Council | 2021-2026 | Central and West Oxford | LCWIP
T71 | Active Travel | LCWIP Route 26: B4044 Community Path from Eynsham - Botley. To be funded by Growth Deal. | Essential | 13000000 | 13000000 | Oxfordshire County Council / Growth Deal | 2021-2026 | Central and West Oxford | LCWIP
T72 | Active Travel | LCWIP Route C: Oxford Ring Road, including the widening and resurfacing of Oxford Ring Road, and traffic calming measures in Wolvercote Village, as well as the Upper and Lower Wolvercote QPC | Essential | 13160000 |  | Oxfordshire County Council | 2021-2026 | North Oxford | LCWIP
T73 | Transport | LCWIP Route CC: City Centre Parking, through delivering the park that Bike proposals | Essential | 75000 |  | Oxfordshire County Council | 2021-2026 | Central and West Oxford | LCWIP
T74 | Transport | City Centre Cycle Hubs Parking | Essential | 2000000 |  | Oxfordshire County Council | 2021-2026 | Central and West Oxford | LCWIP
Education
E1 | Education | 0.5FE expansion to Wolvercote Primary School (1.5-2.0FE), to cater for growth in North Oxford. An updated assessment would need to be undertaken once there is a confirmed timescale for expansion. Timing to be informed by regular monitoring of the demand for school places in the surrounding areas. | Essential | 2,916,04 |  | Oxfordshire County Council / Academy Trust | 2021-2026 | North Oxford | Stakeholder engagement with Oxfordshire County Council
E2 | Education | 0.5FE expansion to Barton Park Primary School (1.5-2.0FE), to cater for growth in East Oxford. Timing to be informed by regular monitoring of the demand for school places in the surrounding area. | Essential | 1970000 |  | Oxfordshire County Council / Developer | 2026-2036 | East Oxford | Stakeholder engagement with Oxfordshire County Council
E3 | Education | There is an exisiting shortage of special school capacity serving Oxford. Options for expansion of capacity are being explored. Due to the nature of special educaiton provision, the additional capacity may be located within or outside of Oxford. | Essential | Dependent on scope and scale |  | Oxfordshire County Council | 2021-2026 | City-wide | Stakeholder engagement with Oxfordshire County Council
Healthcare
H1 | Primary Healthcare | Relocation of Wolvercote surgery to new development at Wolvercote Mill (Noted CCG desire to now amalgamate this into Diamond Place scheme H2 below) - primarily serving existing demand | Essential | Dependent on scope and scale |  | Oxfordshire CCG | 2021-2026 | North Oxford | CCG Localities Plan/stakeholder engagement with CCG
H2 | Primary Healthcare | New health centre in the preferred option of Summertown (Diamond Place), consolidating Banbury Road and Summertown surgeries. Potential to also include consolidation of Wolvercote surgery, previously to have been relocated to Wolvercote Mill development site - primarily serving existing demand | Essential | Dependent on scope and scale |  | Oxfordshire CCG | 2021-2026 | North Oxford | CCG Localities Plan/stakeholder engagement with CCG
Green Infrastructure
GI1 | Green Spaces | Oxford City Biodiversity Enhancements Programme | Essential | 160000 |  | Oxford City Council | 2021-2026 | City-Wide | Oxford City Council identified scheme
GI2 | Green Spaces | Public realm schemes in Central and West Oxford | Important | Dependent on scope and scale |  | Oxford City Council | 2021-2026 | Central and West Oxford | LCWIP and Oxford City Council identified scheme
GI3 | Green Spaces | Improvements in accessibility and biodiversity within Oxpens meadows | Important | Dependent on scope and scale |  | Oxford City Council | 2021-2026 | Central and West Oxford | Oxford City Council identified scheme
GI4 | Green Spaces | Enhancements in the public realm along Oxpens Road to be delivered in tandem with the phases of development that address the Oxpens Road to ensure a high quality environment and setting for maximising the value of new development. | Essential | Dependent on scope and scale |  | Oxford City Council | 2021-2036 | Central and West Oxford | Oxford City Council identified scheme
GI5 | Green Spaces | Port Meadow biodiversity enhancement schemes | Important | Dependent on scope and scale |  | Oxford City Council | 2021-2026 | Central and West Oxford | Oxford City Council identified scheme
GI6 | Green Spaces | Improvements and enhancements to Cutteslowe Park through the Oxford North development | Important | Dependent on scope and scale |  | Oxford City Council | 2021-2026 | North Oxford | Oxford City Council identified scheme
GI7 | Green Spaces | Integrated Green Infrastructure network required for the North of the City, linked with Cherwell sites | Important | Dependent on scope and scale |  | Oxford City Council | 2026-2036 | North Oxford, Cherwell District | Oxford City Council identified scheme
GI8 | Green Spaces | New high-quality public open space to be provided on-site at Osney Mead, as identified within the Local Plan. | Essential | Dependent on scope and scale |  | Delivered through development at Osney Mead | 2021-2026 | Central and West Oxford | Policy SP2: Osney Mead, Oxford local Plan
GI9 | Allotments | Provision of new allotment site at Denny Gardens to address existing under-provision within the city, as identified by the Oxford & District Federation of Allotment Associations. | Essential | £24,500 based on 1ha site, excluding land costs |  | Oxford City Council | 2021-2026 | South Oxford | Oxford City Council / Oxford & District Federation of Allotment Associations
Community Facilities
CF1 | Community Centres | Provision of Blackbird Leys Community Hub as part of wider regeneration efforts within the estate | Important | 550000 |  | Oxford City Council | 2021-2026 | South Oxford | Stakeholder engagement with Oxford City Council / Oxford City Community Centres Strategy
CF2 | Community Centres | Investment into North Oxford Community Centre, to create hub facility with Ferry Leisure centre | Important | 800000 |  | Oxford City Council | 2026-2031 | North Oxford | Stakeholder engagement with Oxford City Council
CF3 | Leisure Centres | Refurbishment and extension of existing Ferry Leisure Centre, linked to adjacent Diamond Place regeneration scheme | Essential | 14000000 |  | Oxford City Council | 2026-2031 | North Oxford | Stakeholder engagement with Oxford City Council
CF4 | Libraries | Improvements to and expansion of Blackbird Leys Library to accommodate demand arising from growth in South Oxford as well as in South Oxfordshire District | Important | Dependent on scope and scale | £1 million secured | Oxfordshire County Council | 2021-2026 | South Oxford, South Oxfordshire District | Stakeholder engagement with Oxfordshire County Council
CF6 | Libraries | Improvements to Headington/,Barton Libraries to accommodate demand arising from growth in East Oxford | Important | Dependent on scope and scale |  | Oxfordshire County Council | 2021-2026 | East Oxford | Stakeholder engagement with Oxfordshire County Council
CF7 | Leisure Centres | Decarbonisation project for Hinksey Pool, with associated works to the adjoining lake, through the use of a local heat network consisting of water source heat pumps and battery / thermal storage, powered by renewable energy. | Important | 1635000 | 1635000 | Oxford City Council | 2021-2026 | South Oxford | Oxford City Council identified scheme
CF8 | Leisure Centres | Improvements to Oxford Ice Rink, which through an options assessment will either be delivered through enhancement works or a full scale redevelopment | Important | Dependent on scope and scale |  | Oxford City Council | 2026-2036 | Central and West Oxford | Oxford City Council identified scheme
CF9 | Community Centres | Provision of a Community Centre for Barton Park, alongside a new local centre | Essential | Dependent on scope and scale |  | Oxford City Council / Barton Park developers | 2021-2026 | East Oxford | Oxford City Council identified scheme
CF10 | Cemeteries | Capacity increases at existing cemeteries within Oxford, including Shotover Cemetery (cross-boundary with South Oxfordshire District Council). Capacity requirements to be established through future Local Plan reviews. | Essential | Dependent on scope and scale |  | Oxford City Council | 2026-2031 | City-Wide | Oxford City Council identified scheme
Utilities
U1 | Electricity Supply | Reinforcements to Yarnton Bulk Supply Point to support identified development quantums within the Oxford North development | Critical | Cost has been estimated to be between £1-5m |  | SSE | 2026-2036 | Cherwell District | Stakeholder engagement with SSE
U2 | Electricity Supply | Uprating of a section of the 132kV cable at Osney Lane Bulk Supply Point (BSP) to accommodate demand from development within the city | Critical | Dependent on scope and scale |  | SSE | 2021-2026 | Central and West Oxford | OxIS (2017) OxIS (2022)
U3 | Electricity Supply | Delivery of a substation required to support the Diamond Place regeneration scheme | Critical | Dependent on scope and scale |  | SSE / Oxford City Council | 2026-2031 | North Oxford | Oxford City Council identified scheme
U4 | Sewerage | Oxford Waste Water Treatment Works (WWTW) upgrade | Critical | Dependent on scope and scale | 41000000 | Thames Water | 2026-2036 | South Oxford | OxIS (2017)
U5 | Flood Risk Defence | Oxford Flood Alleviation Scheme | Essential | 150000000 | Fully funded | Environment Agency / Growth Deal | 2021-2026 | City-Wide | OxIS (2017)
U6 | Digital | Countywide roll out of fibre broadband in commercial buildings, extended where appropriate to surrounding residential buildings. | Important | Dependent on scope and scale |  | Oxfordshire County Council / Openreach | 2021-2026 | City-Wide | Stakeholder engagement with Oxfordshire County Council
W1 | Waste | Redbridge WRC has limited capacity to cope with growing population | Essential/important | Dependedent on if the County Coumcil can find a new site or need to rennovate Redbridge layout to increase capacity. new site will be £4-6million, rennovations could be £2-4million | none as yet. some S106 may be available | OCC | 2024-2030 | 20-30 mins drive time from Redbridge | Oxfordshire county Council/OXIS
|  |  | Critical | Interventions which must take place to allow development to come forward on a specific development site
|  |  | Essential | Interventions which are needed to ensure that the day-to-day needs of residents and businesses can be met, and make development sustainable
|  |  | Important | Interventions which would improve outcomes for residents and businesses, or offer wider sustainability benefits