## Review
Evidence (red = proposed to be discontinued) (orange = not complete agreement between authorities to progress) (Green = potential to progress/complete) | Taken forward without Oxfordshire Plan? (06/09/2022) - updated following HoP and PPM meetings/comments | Current study cost (fee proposal or estimated future cost under OX Plan) | Potential estimated cost of re-scoped work - (based on cost of existing study) | Status | Lead | Contact with consultant following pause and invoices (to be completed when known)
Sustainability Appraisal (SA) | No, as would have involved assessment of broad locations for Oxfordshire Plan which will no longer be needed. SA is specific to the OP2050 policies and strategy and therefore of no value in continuing for Local Plans. | £33,110.83 (fee proposal) |  | Consultant has provided scope and method for the work and meetings attended. Some limited work undertaken on how assessment was to be undertaken and sent to OX Plan team but appraisal not started. Agreement was made with consultant to proceed with SA, but agreed contract was outstanding. | N/A | Progress - what needs to happen next?
OGNA | Current contract with Inceni & Cambridge Econometrics to be ceased, but need to work together on housing need as Local Plans need to progress. | £91,055 (fee proposal) |  | Work undertaken on scope and sent to OX Plan team. Consultants have attended meetings and data gathering had started but substantive work not undertaken. Final method notes from the consultants are available in addition to the brief. Contract in place. | Philip Wadsworth (close down contract) | Invoice received (12/08 - with Tina) from consultant (circa 21K) for steering group meetings and attendance at member workshop which matches contract. Rachel Wileman has approved payment. Consultants have asked about potential for further payment for meetings etc which does not match the staged payment method in the contract which provides for payments after a second workshop and then on the production of a draft report. However, meetings identified in the project plan would have likely been exceeded by the end of the project. Did we respond to thier request in writing - is this on my to do list?
Habitats Regulations Assessment | No, as would have involved assessment of broad locations which will no longer be needed. Joint cumulative impact assessment would not be effective due to different timings on Local Plans. Local Plans to undertake their own HRA's. Some aspects of the early HRA work can steer this process. Some information is available in the stage 1 report at reg 18(2). The screening and risk zones from 2019 are not made out of date by the OP2050 ceasing although some may not reflect recent nutrient neutrality issues. | £102,004 (fee proposal) |  | Consultant has provided scope and method for the work and meetings held. Some information is available in the stage 1 report at reg 18(2). HRA from reg 18(2) and the screening and risk zones from 2019 are not made out of date by the OP2050 ceasing although some may not reflect recent nutrient neutrality issues. Further work was planned at reg 19. Agreement was made with consultant to proceed, but agreed contract outstanding. | Officer needs to assigned to complete and close down contract. Rebekah Goodwill has been the lead cotnact up until the cancellation of the OX Plan. | Any likely cost implications?
Development Potential Study | No, undertaken through city/district HELAAs. Peer review was planned way forward. Each LPA will need to undertake this through the duty to cooperate. | 0 | 0 | Not commissioned. HELAAs progressing (based on jointly agreed methodology). | N/A | N/A
Green Belt Study | Green Belt review could be needed including to explore enhancement potential involving green infrastructure provision but likely to be difficult to produce jointly. Assessment of the Green Belt and/or impacts on it of any development/site options will be assessed through Local Plans instead. | £24,885 (fee proposal) (broad locations assessment only) | 0 | Consultant has provided scope and methodology for the OX Plan to assess broad location options, but no work undertaken. Wider Green Belt review scope was on pause. No agreement or contract with consultant to proceed. |  | What happens next? Any likely cost implications?
Water Cycle Study | County wide study or planned existing baseline information will be beneficial to examine deficiencies/issues for Local Plans. Current scope is not appropriate as it would have involved an assessment of the broad location options for OP2050. Report planned to provide background information on waste water resources and supply, waste water network treatment and capacity, water quality, water neutrality, flood risk, storm overflows, and odour and climate change, constraints and opportunities. This would be useful but would be needed at a district scale instead. Scope of current study will need to re-examined with consultant to facilitate this. | £36,868 (fee proposal) | £10,000 to complete baseline information | Consultant has provided scope and method for the work and meetings held. Some work may have been undertaken on broad locations options appraisal and background work and this was expected imminently. Consultants contacted by CT to check progress on baseline report (22/08/22). Some baseline information is available in the stage 1 report at reg 18 (2). Agreement was made with consultant to proceed. Contract had been sent to the consultant to sign. | Officer needs to assigned an officer to lead on this work. Rebekah Goodwill has been the lead cotnact up until the cancellation of the OX Plan. | Chris Thom contacted consultants but no reply on any progress.
Transport Assessment | No, assessment of the broad locations for the OP2050 is no longer needed. Cherwell has already commissioned work for its Local Plan. OMM model needs progressing quickly for Local Plans. Need to ensure on-going coordination and consistency across the county on transport work such as working group. Information from stage 1 ITP report and good growth principles could be used to inform Local Plans. | £73, 887.50 (fee proposal) (not including use of model) | 0 | Consultant has provided scope and method for the work and meetings held. Workshop held with consultant and county transport colleagues. No other work completed. Agreement with consultant to proceed, but agreed contract outstanding. Meeting with ITP took place to discuss 'decide and provide' guidance on 22/08/22 at ITP's request (so no fee expected) which is planned to be considered at county cabinet later in the year. | James Gagg | Do we have an update on this? Do we need to pay the consultants towards the wortkshop / inception meeting?
Strategic Flood Risk Assessment | Baseline information/mapping being produced for level 1 SFRA. Scope needs to be revisited as broad locations/site assessment no longer required for OP2050. Baseline mapping information to be undertaken to inform Local Plans and/or site assessments asap with aim to be complete by end of September. Chris Brown is keen work continues. Contract arrangements to be explored with consultants to ensure necessary information can be produced on time for Local Plans with aim of producing baseline report in September. Level 2 SFRA's undertaken for Local Plans if needed. S and V should not fund Cherwell site assessments. | £10,765.20 (fee proposal) | £5,000 for completing baseline mapping | Only level 1 SFRA has been commissioned to provide baseline report and assessment of sites. Work being undertaken on baseline flooding situation to inform Local Plans which is approximately a third complete, with most information obtained from the EA. Planned site assessments not started. Oxfordshire Plan sites and Cherwell sites planned to be assessed. Chris Brown has put together list of local flooding incidents for Oxfordshire. Meeting was in diary for Chris Brown to meet with consultants to discuss, but postponed. Timetable was for consultant to produce; baseline maps by end of August, site assessments by early September and draft report mid-September. Contract in place. | Officer needs to assigned an officer to lead on this work. Rebekah Goodwill has been the lead cotnact up until the cancellation of the OX Plan. | Invoice due for £2,153.04 in line with contract which specifies payment after the inception meeting. Payment is progressing. What is the outstanding invoice?
Landscape Study | N/A - consultants not commissioned. Should not be commissioned at County level. Studies to be undertaken for Local Plans where needed. | 15,000 (estimated) |  | No commission. Intended potential commission for broad location assessment for Reg 19 next year.
Viability Assessment | No, viability assessments to be undertaken for Local Plans. As the viability assessment was to assess the OP2050 policies and sites, there is no value to anyone in continuing this commission. | £47,338.19 (fee proposal) |  | Inception meeting held, no substantive work undertaken. Inception meeting note provided by consultant. Draft contract in place as part of procurement process, but final agreed contract outstanding. | Philip Wadsworth | Potential invoice (£9,467.64) for inception meeting due in line with draft contract
Air Quality Impact Assessment | No, to be undertaken through Local Plans instead. Dependent on transport modelling and HRA linkages. Difficult to commission an Oxfordshire wide study if there are different local plan timetables. Impacts can be dealt with under duty to cooperate. | £30,000 (estimated) |  | No commission - intended for reg 19 next year. | N/A
Zero Carbon Study | Could be a need for joint consistent evidence across Oxfordshire e.g. for design and construction/whole life cycle carbon and emissions to inform Local Plans. However robust evidence would be needed considering the Salt Cross decision. Meeting within the next 3 weeks with Bioregional to be arranged to explore potential way forward for evidence to inform Local Plans which is needed asap. Need to explore changing the Bioregional scope document to inform Local Plans and to form the basis of the meeting with consultants. This will assist in determining the way forward on this work including if it can be produced on joint basis. However, joint evidence could mean Local Plans with different timescales would delay progress; therefore not full agreement between authorities to undertake this. | £2,814 (fee proposal) | 10000 | Consultant has provided scope and method for the work and meetings held. The scope is focused around the assessment of the Ox Plan policies through a matrix with baseline information proposed to be provided which would have been the subject of further work. This has been sent to PPM's. No commission, was intended for reg 19 next year. | Depends on outcome of discussion with HOP (9/09/22) | Scheduled meeting with consultants (not clear on who is arranging this and whether this is now going to happen)
OXIS | Infrastructure related to broad locations options not required, but OXIS project should be taken forward as a county project to assist in infrastructure provision for county and Local Plans. How will this be funded? Further discussion needed on way forward. OXIS is separate from the Oxfordshire Plan and OXIS decisions in the past were undertaken by programme board so decisions on its way forward need to be taken outside the PPM group, but PPMs should be involved in discussions on how this will be progressed. It would be beneficial to ensure that there is greater tie up between Local Plans and OXIS going forward. | £47,000 (assigned budget) | 0 | Transport colleagues consulted on transport infrastructure needs/those in the pipeline for broad locations, with the intention of this informing the reg 18 (3) consultation. No consultant commission, was intended for reg 19 next year. | James Gagg / Rachel Wileman | Rachel Wileman is exploring how OXIS can be taken forward. Dawn to discuss with James with a view to having a meeting on the way forward with those that need to be involved.
Gypsy, Traveller and Travelling Showpeople Needs Assessment | County wide study to be required for Local Plans ASAP, but should use different consultants. Because of the nature of assessment and extent of traveller movement across boundaries, a recommission with all Oxfordshire partnership would be beneficial. Need to seek any current information held by consultants to use in a new study and retrieve any money back from consultants where possible. Legal to be involved on this if necessary. West to explore re-commissioning with west's procurement team. Plan team to send Chris H the original brief - has this been done? | 0 | Estimated £20,000 for replacement study | A draft (unpublished report) was completed and paid for which includes some Oxfordshire context. There is missing information - nothing sent to us on the survey results. No further work completed due to consultant unresponsive. Consultant didn’t attend planned meeting on 5 August with no reason given. | Chris Hargraves | Copy of the original contract has been lost and there are no detailed records - is this correct? Need an update on this with Robyn
Health Impact Assessment | Based on wider determinants of health - can be used as a template/useful tool kit for Local Plans and other relevant plans and strategies. Consultants instructed to complete work, but check needed on outcomes. Not needed for broad location options for Oxfordshire Plan. | £5,061 (remaining fee due) |  | Contract in place. Substantial work already completed and paid including published reports at reg 18(2). Consultants instructed to complete current commission including assessment of options with draft report due by end of august. They will try to split out information regarding the spatial options assessment by district, although they state this may be difficult to achieve. |  | Small outstanding payment to be made to complete this work - is this £5061? Outputs of the work have now been completed (as per email from Rosie Rose of 06/09). It should be noted that this does not constitute an HIA of the plan but useful pieces of evidence that could be helpful to the city/districts as they prepare their local plans. Can the full report or parts of it (e.g. scoping) be published on the FOP website on the HIA Toolkit page?
Green Infrastructure Assessment/Nature recovery and natural capital (internal work) | Intent of reg 18(2) was to identify those parts of the county that are important for establishing a well-connected ecological network and use this mapped resource to shape the policies, define the spatial strategy and determine the spatial distribution of development in the OP2050, which should be considered going forward. The proposal was that the OP2050 will utilise the natural capital baseline mapping so that it can be used to guide strategic planning for development and green infrastructure investment. This ambition can still be explored but needed baseline assessment at local level anyway. Further discussion needed on this. This should be considered going forward at a local scale if agreement cannot be made at a county level. Work should be progressed by wider county/Local Nature Partnership. Nick Mottram will be continuing with this and he has put forward a proposal to DEFRA - could be potential for these matters to wrapped up in a county wide green infrastructure study in line with EA and NE advice. Alternatively if district studies are undertaken, checking of consistency should be undertaken (No complete agreement between authorities to progress green infrastructure work). | 0 |  | No consultant involvement. Mapping of draft nature recovery network undertaken. Natural capital baseline work has been produced by Oxford University and Natural England are developing an 'environmental benefits from nature tool'. This was intended to inform the Oxfordshire Plan. | Andrew Thompson - mapping based work (upload and transfer database) | Andrew to make data available on sharepoint. Dawn to check progress on nature recovery work and detail on this with Nick Mottram and arrange a meeting with PPM's in the next three weeks.
Totals
Total current cost of evidence in this table |  | 519788.72
Current cost of studies proposed to continue. (This figure will change based on next row) |  | £102, 508.12
Potential estimated cost of re-scoped work for studies that will continue. (Will need confirming as scope is defined over next few weeks). (Does not include any 'claims' that existing consultant could make for existing work.) |  | 45000
Total cost incurred from current commissioned studies. (Completed as contact made with consultants)
General notes from/following PPM meeting | Needs to be determined the further contact made with the consultants following the 'pause' email where work will not continue. Legal have been consulted and will advise on each discontinued study individually - OX Plan team have sent relevant information to legal. Wherever possible, any existing work completed by consultants should not be lost. There is a need to progress studies that remain asap to inform Local Plans. Needs to be determined, with senior officers if necessary, who will generally take forward the studies that will be retained in the short and long term as cited above. PPM meeting for Oxfordshire Plan to be stopped and OPPO to take over. Could be merit in making OPPO slightly more frequent. Phil to ask Paul to cancel PPM meetings. How can the work undertaken on the OX Plan policies be used and/or taken forward such as on the circular economy. West is undertaking a consultation over the next few weeks where this information will be useful. Phil circulated a version of the plan which will be banked and used subsequently to inform Local Plans. No detailed plans were made for the consultation on the OX Plan, such as venue booking, that was due to occur in the autumn but a draft communications strategy was produced. Discussion needed with senior officers on communication of the discontinuation of the Plan with Duty to Cooperate partners. Filing – CT is saving main information on the X drive but may not have access to all information which could be elsewhere such as on emails. Dawn has access to the X drive and will be able to retrieve information going forward when it is needed. OX Plan information should be retained and transferred to: Planning and place, strategic infrastructure and planning, strategic planning where Dawn can access it.
564788.72